Table of Contents

# KRISHI-VERSE — BUILD PLAN (turning the skeleton into the platform)

Read this with apps/api/src/modules/listings/ open — that is the pattern every module copies.

## The reality (so nobody is surprised)

- The repo is a complete, correct skeleton: ~250 DB tables (real SQL, seeded), 2,497 named files, one fully-built reference module (listings), and the laws/CI that keep it consistent.

- Filling it is ~400k–900k lines of code = your Survival Guide’s 9-month Phase-1 with a 6-person team, then years for Phases 2-3.

- This plan makes that execution systematic: a fixed build order, a copy-paste pattern per module, AI-agent briefs, and gates so quality never drifts.

## Build order — dependency-respecting (do NOT reorder)

Foundations first; money early; then the Phase-1 revenue loop; defer the rest.

### WAVE 0 — Platform plumbing (no business value alone, everything depends on it)

| Order | Area | Where | Why first |
| --- | --- | --- | --- |
| 0.1 | core/config, core/database (pool, RLS session, uuid, partition-prune, txn) | apps/api/src/core | nothing runs without DB + tenant context |
| 0.2 | core/tenancy-context, core/auth, core/rbac | apps/api/src/core | every request needs tenant + identity + permission |
| 0.3 | core/outbox, core/idempotency, core/http, core/cache | apps/api/src/core | the laws (events, idempotency, envelope, cache) |
| 0.4 | core/quota, core/resilience, core/backpressure | apps/api/src/core | scale + safety wrappers |
| 0.5 | apps/wallet-service (ledger, accounts, recon, gRPC) | apps/wallet-service | money isolation — build before any module moves money |
| 0.6 | apps/outbox-relay | apps/outbox-relay | reliable events out |
| 0.7 | packages/contracts, packages/config | packages | shared DTOs/events + lint laws |

### WAVE 1 — Phase-1 revenue loop (the MVP: list → sell → pay → wage)

| Order | Module | Effort* | Notes |
| --- | --- | --- | --- |
| 1.1 | identity | L | users, dynamic RBAC, KYC, sessions, consent |
| 1.2 | tenancy | L | plans, subscriptions, settings, flags |
| 1.3 | catalogue | M | category tree + attributes (mostly admin CRUD) |
| 1.4 | listings | DONE | the reference module — already built |
| 1.5 | payments (+ wallet integration) | XL | the money path; CODEOWNERS-gated |
| 1.6 | orders | XL | multi-item, escrow, state machine, partial fulfil |
| 1.7 | auctions | L | real-time bids (pairs with realtime-gateway) |
| 1.8 | logistics (basic) | M | self-pickup + tenant delivery + OTP/POD |
| 1.9 | labour | XL | the differentiator; dignity CHECK, geofence, same-day wage |
| 1.10 | communication + notifications | M | templates, SMS/WhatsApp/push via worker |
| 1.11 | reviews, disputes | M | trust loop |
| 1.12 | ambassadors | M | onboarding + commissions |
| 1.13 | market-intel (mandi prices) | M | ingestion + read-model |
| 1.14 | land-soil-weather (weather only) | S | advisory push |
| 1.15 | admin-api (god mode core) | L | tenant approve/suspend/impersonate/billing |
| 1.16 | apps/realtime-gateway | M | live auctions/order tracking |
| 1.17 | apps/worker (Phase-1 jobs) | L | settlements, notifications, partitions, recon |
| 1.18 | apps/mobile (Phase-1 features) | XL | farmer/buyer/worker/ambassador screens |
| 1.19 | apps/web-tenant (Phase-1 routes) | L | the tenant console |

### WAVE 2 — Phase-2 modules (after MVP traction)

livestock, dairy, fintech, schemes, equipment, warehousing, contract-farming, memberships, promotions, services-marketplace, requirements(full), offers(full), stream-processor, whatsapp-bot, ivr-ussd-gateway, analytics-pipeline, web-partner, ai-services.

### WAVE 3 — Phase-3

exports, traceability(full), carbon, cells (international), federated learning.

Effort: S=1-3 days · M=1-2 weeks · L=2-4 weeks · XL=4-8 weeks (one senior engineer/AI-pair).

## Milestone gates (do not pass a gate with the previous one red)

- G0 (end Wave 0): a request flows api→DB with tenant context; wallet posts a balanced txn; outbox event published; CI green incl. tenant-isolation + ledger-invariant suites.

- G1 (end Wave 1): the full loop works end-to-end in staging — farmer lists (voice), buyer buys, escrow holds, delivery confirmed, seller paid, worker booked + same-day wage; 50 fake transactions, zero payment failures; load test k6-order-flow p95<500ms.

- G2: Phase-2 modules live; ONDC/WhatsApp; fintech first loan; k6-billion-scale model run against a staging cell.

- G3: Phase-3 + first international cell.

## The 1% that is already done carries the 99%

listings proves every pattern (state machine, BIGINT money, outbox-in-txn, idempotency, quota, shard router, read-model, tenant-isolation test). Every other module is “copy listings, change the entity, follow its README.” That is why the skeleton matters: the hard thinking is finished; what remains is disciplined typing. # How to Build a Module with an AI Coding Agent (Claude Code / Cursor / etc.)

You will build most of this with AI agents. This is the exact, repeatable recipe so every module comes out consistent and correct. One module per agent session.

## The brief (paste this, fill the [BRACKETS])

You are implementing the [MODULE] module of Krishi-Verse, a multi-tenant agri-commerce platform. Before writing code: 1. Read /CLAUDE.md — the 12 laws are non-negotiable constraints. 2. Read /apps/api/src/modules/listings/ IN FULL — it is the gold-standard pattern. Your module must match its structure and patterns exactly. 3. Read the DB tables for this module in /db/migrations/ (see the file named for your domain) — those are the real columns; money is BIGINT minor units. 4. Read /docs/architecture/module-map.md for which PRD module + screens this serves.

Then implement [MODULE] to the SAME depth as listings: - domain/*.entity.ts (pure TS, no framework, 95% unit-tested) - domain/*.state.ts for any status field (the ONLY place transitions live) - repositories/*.repository.ts — tenant-scoped, shard-routed, reads on replica - services/*.service.ts — use-cases; writes + outbox events in ONE transaction; idempotency on mutations; quota where it applies - read-models/* for any list/search/dashboard read path - controllers/v1/*.controller.ts — validate→authorize→delegate only - events/handlers/* for events this module consumes (idempotent) - jobs/* for any cron/queue work (runs in apps/worker) - policies/*.policies.ts — permission codes (from DB, dynamic RBAC) - __tests__/tenant-isolation.spec.ts is MANDATORY and must actually assert cross-tenant denial.

Money moves ONLY by calling the wallet-service gRPC client — never INSERT into ledger tables. Emit events via the outbox in the same txn — never dual-write. Output: implement every file, then run the module’s tests and the repo’s tools/scripts/verify-structure.sh.

## Review checklist (you, the founder/CTO, before merge)

- ☐ Matches the listings file layout exactly

- ☐ No raw query without tenant scoping (the tenant-guard lint rule catches most)

- ☐ No number/float for money — only bigint minor units

- ☐ Status changes go through the state machine, nowhere else

- ☐ Every write others care about emits an outbox event in the same transaction

- ☐ Mutations accept Idempotency-Key

- ☐ tenant-isolation.spec actually fails when given another tenant’s id

- ☐ No import of another module’s repository (only its service/events)

- ☐ i18n keys for user-facing text, not literals

## Pace & sequencing

- Do modules in the BUILD_PLAN order. A module’s dependencies must be built first (e.g. payments before orders, wallet-service before payments).

- One module ≈ one to a few agent sessions + your review. Budget per the effort column in the build plan.

- After each module: run its tests, deploy to staging behind a feature flag (OFF), enable for the demo tenant, smoke-test, then turn the flag on gradually. # Realistic Effort, Team & Timeline (founder-honest)

## What’s left, in plain numbers

- Skeleton + DB + 1 reference module + seeds + laws/CI = DONE (the hard architecture).

- Remaining = implementation: ~400k–900k lines across ~2,470 files.

## This matches your own Founder OS exactly

- Phase 1 (Wave 0+1): 9 months, 6 people (CTO + 3-4 engineers + designer), per your Survival Guide and Field Manual. Reaches the MVP loop + first 5 tenants.

- Phase 2 (Wave 2): ~12 months, team grows to ~15-25 (Master Roadmap Year 2).

- Phase 3 (Wave 3): Years 3-5, larger org.

## How AI agents change the math (they help, don’t replace)

With disciplined AI-pair building (the recipe in 01_AI_AGENT_BUILD_GUIDE), a senior engineer can plausibly go 2-3× faster on CRUD-heavy modules — but money, auth, labour-dignity, and real-time code still need careful human review and testing. Estimate: AI-assisted, a strong CTO + 2 engineers could reach G1 (MVP loop) in ~4-6 months instead of 9. Do NOT let AI write the wallet/ledger unreviewed.

## First 3 hires (from your Hiring Plan, Doc 10), in order

- CTO / co-founder — has shipped multi-tenant SaaS; owns Wave 0 + wallet-service.

- Senior full-stack engineer — Wave 1 modules alongside CTO.

- Mobile engineer (React Native) — apps/mobile Phase-1 features. Then designer (contract), then backend/devops (#5), per the Field Manual sequence.

## How to hand them this repo (day 1)

- They clone, run docker compose up, node db/scripts/migrate.js, node db/scripts/seed.js.

- They read CLAUDE.md, the listings module, and docs/build/00_BUILD_PLAN.md.

- They pick up Wave 0 tickets (02_MODULE_TICKET_TEMPLATE per area).

- They update 03_BUILD_STATE as they go.

## The honest bottom line

You do not have a finished billion-user platform — nobody could hand you that in any number of chat sessions. You have something rarer and more useful at Day 0: a correct, scale-ready blueprint and reference build that a competent team can execute in your planned timeline without hitting a re-architecture wall. That is the difference between this and a “local-level” project — not the line count today, but the fact that every line they add fits a system designed for billions.